## Forward plan 2627
Last updated April 2026
Key Descriptions | Key Colour Code | Public Transport Statistics and Road Network and Condition Statistics Forward Work Plan (April 2026 - March 2027)
Planned work
Work to be confirmed
Work completed
Work Area | Forward Work Plan | Lead | Actions required to progress work programme | Updates / Links to relevant information / development
[5 empty] | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01
Public Transport Statistics | Preparation of Annual Public Transport Statistics Northern Ireland Accredited Official Statistics | Deputy Principal Statistician | Publish latest data on Public Transport Statistics | Latest publication available on the DfI website | bar: 2026-07-01 to 2026-09-01
Public Transport Statistics | Key stakeholder / data provider meetings | Principal Statistician | Arrange meetings with key stakeholders to discuss Annual Public Transport Statistics Northern Ireland Accredited Official Statistics | bar: 2026-05-01; 2027-03-01
Public Transport Statistics | Review of Quality Assurance of Administrative Data Sources (QAAD) report | Deputy Principal Statistician | Review with customer and update report accordingly | Current QAAD report is available on the DfI website | bar: 2026-08-01 to 2026-09-01
Public Transport Statistics | Review of Background Quality Report (BQR) | Deputy Principal Statistician | Review with customer and update report accordingly | Current BQR is available on the DfI website | bar: 2026-08-01 to 2026-09-01
Public Transport Statistics | Attendance at Public Transport Monitoring groups | Deputy Principal Statistician | Attend meetings and provide statistical advice as required | Results of Publc Transport monitoring are published on the Translink website | bar: 2026-05-01; 2026-08-01; 2026-11-01; 2027-02-01
Public Transport Statistics | Transport Accessibility Stats | Deputy Principal Statistician | Ongoing maintenance of useful links page | Useful links page is available on the DfI website | bar: 2026-05-01; 2026-08-01; 2026-11-01; 2027-02-01
Road Network and Condition Statistics | Preparation of Annual Northern Ireland Road Network and Condition Official Statistics | Deputy Principal Statistician | Publish latest data on Road Network and Condition Statistics | Latest publication available on the DfI website | bar: 2026-09-01 to 2026-11-01
Road Network and Condition Statistics | Key stakeholder meetings | Principal Statistician | Meet with key stakeholders to discuss Annual Northern Ireland Road Network and Condition Official Statistics & Data Visualisations | bar: 2026-05-01
Road Network and Condition Statistics | Review of Quality Assurance of Administrative Data Sources (QAAD) report | Deputy Principal Statistician | Review with customer and update report accordingly | Current QAAD report is available on the DfI website
Road Network and Condition Statistics | Review of Background Quality Report (BQR) | Deputy Principal Statistician | Review with customer and update report accordingly | Current BQR is available on the DfI website
Road Network and Condition Statistics | Review of Technical Report | Deputy Principal Statistician | Review with customer and update report accordingly | Current Technical Report is available on the DfI website
Road Network and Condition Statistics | Review of Process Maps | Deputy Principal Statistician | Review maps with customer and update accordingly | Current Process Maps are available on the DfI website
Road Network and Condition Statistics | Data visualisations for road condition data on NISRA data portal | Deputy Principal Statistician | Upload latest data to data portal | Data are available on the NISRA data portal
Road Network and Condition Statistics | Review LGD infographics | Deputy Principal Statistician | Review with customer and make changes accordingly | Current LGD infographics are available on the DfI website
Road Network and Condition Statistics | Dashboard for road condition data on NISRA data portal | Deputy Principal Statistician | Upload latest data to data portal for dashboard to be updated accordingly | Roads data dashboard
Note: this forward work plan relates to external publications; internal statistical support work is not included