## Forward plan 2425
Last updated 28/03/2024
Key Descriptions | Key Colour Code | Northern Ireland Planning Statistics Forward Work Programme (April 2024 - March 2025)
Planned Work
Work underway
Complete
Work on hold
Forward Work Plan | Lead | Actions required to progress work programme | Updates / Links to relevant information / development
Ongoing Actions: |  | Forward Work plan |  | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01
Publication of Quarterly & Annual Planning Official Statistics | DP Statistician | Continuing as per usual intervals, on a quarterly basis. Publication normally during March, June, September and December each year.
Annual Publication of Planning Applications Open Dataset | DP Statistician | Publishing annually following the publication of the NI Annual Planning Statistics. Available information can be found at this link: | bar: 2024-07-01
Production of Monthly MIS reports on Legislative Indicators - Department & Councils | DP Statistician | Ongoing in support of each quarterly publication
Production of validated quarterly OS datasets - Department & Councils | DP Statistician | Ongoing in support of each quarterly publication | bar: 2024-03-01; 2024-07-01; 2024-09-01; 2024-12-01; 2025-03-01
Input to the development of a new planning IT systems to ensure analytical output and other ASRB requirements | DP Statistician | Work is ongoing to develop a fuller range of enforcement statistics. | The new Mid Ulster system went live on 22 June 2022 and the NI Planning Portal went live on 5 December 2022; extracts have been developed from both of these systems to enable Planning Statistics to be produced. | bar: 2024-01-01 to 2024-07-01
Attendance at Cross-Government Housing Statistics working group | DP Statistician | Head of Section to attend meetings as required. Meetings held quarterly. |  | 2024-01-01: Cross Govt Working Group Meeting; 2024-05-01: Cross Govt Working Group Meeting; 2024-09-01: Cross Govt Working Group Meeting; 2024-12-01: Cross Govt Working Group Meeting
Routine update of published Ad hoc Planning Queries | DP Statistician | Quarterly update of published Ad hoc Planning Queries. | bar: 2024-03-01; 2024-07-01; 2024-10-01; 2025-01-01
Provision of Northern Ireland Planning Statistics to the NISRA Data Portal (which replaced the Northern Ireland Neighbourhood Information System (NINIS) in summer 2023) | DP Statistician | Ongoing in support of each annual publication. Develop and publish additional data by Assembly Area on the NISRA data portal. | Statistics successfully developed and delivered to the NISRA data portal in September 2023, including statistics for 2022/23. Annual suite of outputs following publication of finalised annual NI Planning Statistics can be found on the NISRA data portal here: https://data.nisra.gov.uk/table/PADELGD Assembly Area level output can be found here: https://data.nisra.gov.uk/table/PADAA | bar: 2024-07-01 to 2024-08-01
Review of Quality Assurance of Administrative Data Sources (QAAD) | DP Statistician | Current version | The document is overdue review. The reason for delay had been to give time for the new planning portals to go live and become fully operational. Due to staffing resource this is delayed but will remain on the work plan and actioned as resource allows.
Review of Background Quality Report (BQR) | DP Statistician | Current version | The document is overdue review. The reason for delay had been to give time for the new planning portals to go live and become fully operational. Due to staffing resource this is delayed but will remain on the work plan and actioned as resource allows.
Carry out Planning Statistics User Survey | DP Statistician | Carry out user consultation of planning statistics | ASRB carried out a user consultation exercise during the summer 2023. This is now complete and the outcome report was published on 12/10/2023 and can be found on the main planning activity website page. Date of next user survey to be decided.
Exploration of viable options and development of interactive Planning data visualisations | DP Statistician | Develop and publish new interactive planning statistics content. | ASRB engaged with users during the summer 2023. Feedback highlighted there was a user need for interactive publications. ASRB have shortened the current quarterly publication to create resource to explore and develop interactive content. This work is planned to commence in early 2024. Due to staffing resource this is delayed but will remain on the work plan and actioned as resource allows.
Exploration of Reproducible Analytical Pipelines (RAP) processes | Principal Statistician | Head of Branch engaged with Office for Statistical Regulation (OSR) review of RAP processes during October 2020. ASRB Staff have all attended Intro to R training to commence skilling to allow future development of RAP processes, as resource allows. | Due to staffing resource this is delayed but will remain on the work plan and actioned as resource allows.